## Sheet1
excel work
log analysis
documentation
testing
url update analysis on sites
instance pe scripts run
instance pe editing of scripts
instance creation
automation script for retreiving data from excel and dividing into batches
release miration- script ananlysis, log anaylsis, testing with new repos's and files
flow chart and documentation of a script
resolved multiple errors for testing scripts
collected data from all team members
tested script, got error, found error in script, resolved error by modifying script and tested again. This was for migration utiltiy and wrapper script
used winscp to log into instance and edited/download data for further processing
created multiple commands based on the script and conditions to run a script
reduce api calls from a script, ways to do that and edit the script accordingly
git filter repo task, large fileuploaded, after multiple commits and changes to file, commit history deleted from github using this utility, push changes to branch
do all required installations in ec2 instance
created a script for this: synced data from source to target, then target to source, made them equal and then finally archived the target
backout script : sub-process something task

## Sheet2
Sprint | User Story ID | User Story Title | Task Description | Approach / How I Worked | Remarks
Iteration2025.2.3 | US162017 | [Pre-pilot]Migrate missing 13 teams | The task required me to use a python script, to migrate 13 teams to the target organisation | The first step was to cross check the teams in the source organisation. If the team is there then check if there are members available or not. Once that was confirmed, I was given the command to run the python script. For the command I had to prepare an input file with all the team names which were supposed to be migrated. The input file will be a part of the command as one of the parameters. Before that I was supposed to export tokens of the source organisation which was GHES and the target organisation which was GHEC. Once I exported the tokens, I ran the command in the gitbash to migrate those teams. The script which I used to migrate the teams is gh_team_migration_idp_group_map.py. | It was my first task in my first client based project. It took me a while to understand how the script works and how I should run all other scripts. So for me it was a bit slow paced.
Iteration2025.2.3 | US162018 | [Pre-pilot]Set up Additional EC2 instances | Setup five additional EC2 instances for the migration team using the existing IaC pipeline and validate that the environment is ready for upcoming migration activities. | I had to set up 5 EC2 instances. For that I had to login to my aws account and navigate to AWS access portal, after that I had to search service catalog, set US east 1 as my location, navigate to the provisioned products. I was given a set of instruction guideline, according to that I had to choose the pipeline and the versions, and according to the guideline I created the EC2 instances with all the details given to me in the guideline. Once created, I had to validate those EC2 instances. Once the validation were done, I had to set up the SSH key pairs of 5 team members of our project using their .pem key file. I got a set of commands to run set the ssh key pairs. Once it was done, I was supposed to run a sample migration | This task was interesting, I got my hands on experience on using AWS for creating EC2 instances. It took me long hours to complete this task but I was able to do it easily with the help of one of my team member who guided me to create it. She created one sample instance and after that I created 5 official instances
Iteration2025.2.4 | US161497 | [GHEC]Pilot Batch 5 Initial Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to sandbox organisation. We had configured an initial json file and that json file will be one of the input for our wrapper_script_initial.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration2025.2.4 | US163079 | [GHEC] Initial Migration Testing and Validation | If any repository failed during final migration, we are supposed to remigrate them again using the same steps. Those which got migrated, we need to check all the settings frrom the GUI and make a documentation on that | Simple task, if failed do the migration steps again by excluding the successful ones. | The task was simple and was done without any issues
Iteration 2025.2.5 | DE4667 | [Pilot] Old github links in github repo wiki | Query from the user: is there any easy way to modify them all (to point to the new repo) or do we need to go to each document and repoint the links to the new location? | I just needed to update the wiki script to update the url where it only updates the .md file to update .md along with .adoc files | Simple task. Took me few hours to update the script
Iteration 2025.2.5 | US162997 | [GHEC]Pilot Batch 5 final Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple but we were facing a lot of complications. The scripts were failing continuously. Worked for 18 hours straight
Iteration 2025.2.6 | DE4668 | [Pilot] Embedded images in the loadtest aren't loading after migration | To check why the image url are not getting updated after migration | I did RCA of this defect. The repository after migration were not able to see the images was because they had stored the image externally and our script is not handling that. So once the repository is migrated, they need to update the image url manually. | Simple task but took a while to get the conclusion
Iteration 2025.2.7IP | US163221 | [Wave 1] Batch 5 - Initial Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to sandbox organisation. We had configured an initial json file and that json file will be one of the input for our wrapper_script_initial.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.2.7IP | US163247 | [Wave 1] Batch 5 - Testing and Validation | If any repository failed during initial migration, we are supposed to remigrate them again using the same steps. Those which got migrated, we need to check all the settings frrom the GUI and make a documentation on that | Simple task, if failed do the migration steps again by excluding the successful ones. | The task was simple and was done without any issues
Iteration 2025.3.1 | US163241 | [Wave 1] Batch 5 - fINAL Migration and Validation | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.3.2 | US163684 | [Wave 2] Batch 5 - Initial Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to sandbox organisation. We had configured an initial json file and that json file will be one of the input for our wrapper_script_initial.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.3.2 | US163671 | [Wave 2] Batch 5 - fINAL Migration and Validation | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.3.2 | US163673 | [Wave 2] Batch 5 - Testing and Validation | If any repository failed during initial migration, we are supposed to remigrate them again using the same steps. Those which got migrated, we need to check all the settings frrom the GUI and make a documentation on that | Simple task, if failed do the migration steps again by excluding the successful ones. | The task was simple and was done without any issues
Iteration 2025.3.3 | DE5246 | Issue: Unable to Clone Repository Due to Port 22 Blocked (SSH Failure) | The user was unable to clone the GitHub repository using the SSH URL because port 22 was blocked by the company firewall. Attempts to clone via SSH resulted in timeouts and access errors. | Since SSH traffic on port 22 is blocked, the user cloned the repository using the HTTPS URL instead of the SSH URL. Documentation was shared to guide the user on authenticating and cloning via HTTPS or GitHub CLI. | I learned that SSH cloning fails when port 22 is blocked by the firewall, and using the HTTPS clone URL is the correct workaround. This helped me understand how network restrictions impact Git operations.
Iteration 2025.3.3 | US164044 | [Wave 3] Batch 5 - Initial Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to sandbox organisation. We had configured an initial json file and that json file will be one of the input for our wrapper_script_initial.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.3.4 | DE5554 | Issue 248: <repo_name> archived but we never did | After migrating the repository to the cloud, the repo was found to be in an archived state, preventing the user from accessing it or creating issues. The team needed to investigate why the repository was archived without any intentional action. | The repository was manually unarchived to restore access, and audit logs were reviewed to identify whether the action was performed manually by a user or triggered by an automation script. | The repository was archived unintentionally. Audit log verification was performed to determine the root cause and confirm whether it resulted from manual activity or automation.
Iteration 2025.3.4 | US164048 | [Wave 3] Batch 5 - fINAL Migration and Validation | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.3.4 | US164052 | [Wave 3] Batch 5 - Testing and Validation | If any repository failed during initial migration, we are supposed to remigrate them again using the same steps. Those which got migrated, we need to check all the settings frrom the GUI and make a documentation on that | Simple task, if failed do the migration steps again by excluding the successful ones. | The task was simple and was done without any issues
Iteration 2025.3.5 | DE5711 | Issue 276: <User_name> can't access the new SaaS platform | The user's Id was not able to surpass the sso link to the target organisation | We checked the user's name and id in our active directory and the user was not a part of any gh-* groups, so we asked the user to raise a ticket to be a part of those gh-* groups which are associated with the repo he needs to work on | I got to know that a user may or may not be a part of the gh-* groups, which is a mandatory step to access the cloud SaaS platform, so if we get these kind of issues then we should also check our active directory with the user's details to find the root cause
Iteration 2025.3.5 | US164454 | [Wave 4] Batch 5 - Initial Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to sandbox organisation. We had configured an initial json file and that json file will be one of the input for our wrapper_script_initial.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.3.5 | US164459 | [Wave 4] Batch 5 - fINAL Migration and Validation | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.3.5 | US164449 | [Wave 4] Batch 5 - Testing and Validation | If any repository failed during initial migration, we are supposed to remigrate them again using the same steps. Those which got migrated, we need to check all the settings frrom the GUI and make a documentation on that | Simple task, if failed do the migration steps again by excluding the successful ones. | The task was simple and was done without any issues
Iteration 2025.3.5IP | DE5777 | Issue 292: <org/repo_name>- Repo not migrated | The repo was somehow skipped from our automation input file generator script to be included in our list of migrated repositories, so the repo user request to migrate the repo as offcycle migration | We just ran our migration script individually for this repo | Even one repo can be missed from our automation script, so we should keep tally of our count
Iteration 2025.3.5IP | DE5769 | Issue 289: Github sso: login issue | The user's Id was not able to surpass the sso link to the target organisation | The user had already shorten their email address to make it under 39 characters to fill the criteria for sso link, but the problem was it was not their main email address, so to make it their primary email address, the user also had to change their UPN(User profile name) name | User can also be removed from gh-* groups due to long email address, long names and there are many other criterias that a user must follow which we had mentioned and prepared in out Github Licensing document
Iteration 2025.3.5IP | DE5726 | Issue 280: <repo_name> seems to be missing in GHEC | The repo was not part of any waves which we have done the migrations till date, it is listed in exception wave | Just some query from users regarding migration | Validating the repo names from our migration sheet is also important
Iteration 2025.4.1 | US164097 | [Wave 5] Batch 5 - Initial Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.4.1 | US164912 | [Wave 5] Batch 5 - Testing and Validation | If any repository failed during initial migration, we are supposed to remigrate them again using the same steps. Those which got migrated, we need to check all the settings frrom the GUI and make a documentation on that | Simple task, if failed do the migration steps again by excluding the successful ones. | The task was simple and was done without any issues
Iteration 2025.4.1 | US164918 | [Wave 5] Batch 5 - fINAL Migration and Validation | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.4.2 | DE6006 | Issue 328: After SaaS migration we have issue in provisioning On-prem VM provision | After migration they were still trying to access the repo through the on-prem url. | They should first login through sso for cloud and then search the repo name their and they will get their repo in the ui | User query which was simple and solvable without much work
Iteration 2025.4.2 | US184298 | [Wave 5B] Batch 5 - Initial Migration | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.4.3 | US176603 | Offcycle Migration Batch 2- part 2 | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | User query which was simple and solvable without much work
Iteration 2025.4.3 | US180088 | [Wave 5B] Batch 5 - fINAL Migration and Validation | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.4.4 | US186596 | [Offcycle Migration] Migration Execution | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.4.5 | US188804 | [SPIKE]: Generate excel report for branches and their owners | Identify all branches in the repository, extract branch details (branch name, committer/owner, last commit date), and generate a CSV/Excel report highlighting stale branches that haven't been updated within the defined threshold. | Mirror‑clone the repository into an EC2 instance and use Git commands to extract the required metadata for each branch, then compile the results into a CSV report. | Learnt a lot of commands which can give such results by not necessarily prepare any script to find these out
Iteration 2025.4.5 | US189065 | [Offcycle Migration] Migration Execution | I was given a list of repositories as an input file. I am supposed to migrated those repos from production source organisation to target organisation. We had configured an final json file and that json file will be one of the input for our wrapper_script_finall.py script. Before that I had to export the tokens for the respective organisation in my EC2 instance and then run the command for the script which uses the json file. |  | The task was simple and was done without any issues
Iteration 2025.4.6IP | US189135 | Issue 385: [PE Consultation] Github Cloud Access Issue | The user is unable to access GitHub Cloud and SSO‑based cloud resources because their UPN(User profile name) account name does not match the newly updated primary email address. To resolve the issue, the user must update their UPN(User profile name) name to align with the new email, after which they can be successfully added to the required gh-* AD groups and regain access through SSO. | Update the user's UPN(User profile name) name to reflect the new primary email address, validate the update in the identity system, and then re‑add the user to the appropriate gh‑* groups to restore GitHub Cloud and SSO access. | The issue occurred because the UPN(User profile name) name was still tied to the old email address. Once identified, we confirmed that updating the UPN(User profile name) and re‑mapping group memberships resolves the access problem.
Iteration 2025.4.6IP | US185978 | [GHEC] Support for failed repos - part 5 | I was give a list of repos which failed multiple times in our migration waves | We had to figure out the root cause on why the repos were getting failed | I had to go in depth with all the logs generated by the migration scripts and find the exact reason. Turns out the repo size was way too big for migration
Iteration 2025.4.7IP | US191536 | Support for failed repos part 2 | I was give a list of repos which failed multiple times in our migration waves | We had to figure out the root cause on why the repos were getting failed | I had to go in depth with all the logs generated by the migration scripts and find the exact reason. Turns out the repo size was way too big for migration
Iteration 2026.1.3 | DE6783 | #468: Push access and repo accessibility issue | The users were not able to push in protected branches | The group which has the write access for push access were empty, so the users have to raise an RITM to get that access | Post migration query checking
Iteration 2026.1.3 | US193745 | [GHES Decommision] Create automation for GHES repositories backup | Build an automation to archive GHES (on‑prem) repositories by deep‑cloning each repo (all branches/tags/history), packaging the output, and uploading the artifacts to an Amazon S3 bucket for long‑term retention prior to GHES decommissioning. | Create a Python script using pandas that reads an input file containing <org_name/repo_name>, uses exported on‑prem tokens to mirror‑clone each repository on an EC2 instance, generates a CSV report, and then uploads the archived repositories to S3 using the provided AWS account details, IAM role, KMS key, and bucket name. | Tokens and AWS details must be securely sourced, and the output should be verified to ensure all repositories are cloned and uploaded correctly before GHES decommissioning.
Iteration 2026.1.4 | US190960 | Decommision Prod GHA runners | This task involves decommissioning the Production GitHub Actions (GHA) runners that are currently connected to the GHES environment. The goal is to unregister and remove all on‑prem runners—specifically those hosted on EC2 and ECS—to support the migration to GitHub Enterprise Cloud and eliminate dependencies on the legacy GHES platform. | Identify all prod GHA runners linked to GHES and systematically unregister them using the appropriate GitHub API/CLI steps, followed by shutting down and cleaning up the underlying EC2/ECS resources to ensure they are fully removed from the GHES environment. | The decommissioning was completed after validating that no workflows were using these runners, and the cleanup ensured all GHES‑linked runners were safely unregistered and retired.
Iteration 2026.1.4 | US195412 | [GHEC] Migrate Secret remediated repos without udeploy components dependency part-1 | I had a list of repos whose secrets were remediated, and had to do offcycle migration like before with all the steps we did in migration cycles |  | The task was simple and was done without any issues